## Sheet1
Effort (Person hours)
MAIN ACTIVITY (Use the WBS to Update) | Sub-tasks | Heena Khan (Project Manager) |  | Bhavna Kumari (Requirements Engineer) |  | Teja Tatimatla (Solutions Architect) |  | Vineet Agarwal (Developer) |  | Abhigna Kandala (Developer) |  | TOTAL ESTIMATED EFFORT per activity | TOTAL ACTUAL EFFORT per activity
| Sub-tasks | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual
Project Management Plan | Draft PMP (Structure, purpose, Context) |  |  | 8 | 7 | [6 empty] | 8 | 7
| Create Work Breakdown Strcuture (WBS) | [6 empty] | 8 | 7 |  |  | 8 | 7
| Develop RACI Matrix | 6 | 6 | [8 empty] | 6 | 6
| Risk Register Preparation |  |  |  |  | 8 | 8 |  |  |  |  | 8 | 8
| Preparation of Figures | [8 empty] | 8 | 8 | 8 | 8
| Progress Tracker SetUp | 2 | 2 | [8 empty] | 2 | 2
| Review & Finalize PMP Document | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 10 | 10
Requirements | Conduct stakeholder interviews & surveys | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12
| Document functional requirements | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 10 | 10
| Document non-functional requirements and design constraints | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 10 | 10
| Build requirements traceability matrix (RTM) | 0 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5
| Validate requirements with stakeholders | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 10 | 10
| Analysis | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 10 | 10
Design | Ux design | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 22 | 22
| Architecture design | 4 | 4 | 4 | 4 | 6 | 6 | 4 | 4 | 4 | 4 | 22 | 22
| Database design | 2 | 2 | 2 | 2 | 2 | 2 | 6 | 6 | 2 | 2 | 14 | 14
| Architecture documentation (SAD) | 6 | 6 | 2 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 16 | 18
| Detailed design (SADD) | 4 | 2 | 4 | 2 | 6 | 2 | 4 | 2 | 4 | 2 | 22 | 10
Implementation | Setup | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 10 | 10
| Module development | 3 | 3 | 4 | 4 | 2 | 2 | 4 | 4 | 4 | 4 | 17 | 17
| Integration | 4 | 1 | 4 | 1 | 4 | 1 | 4 | 1 | 4 | 1 | 20 | 5
| Code quality | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 10 | 0
Testing | Unit testing | 4 | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 12 | 2
| Integration testing | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 10 | 0
| System testing | 2 | 0 | 2 | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 12 | 0
| Acceptance testing | 2 | 0 | 2 | 0 | 4 | 2 | 2 | 0 | 2 | 0 | 12 | 2
| Execute functional tests | 2 | 1 | 2 | 1 | 2 | 1 | 4 | 2 | 2 | 1 | 12 | 6
| Conduct non-functional tests | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 4 | 2 | 14 | 14
| Analyze test coverage reports | 4 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 14 | 14
| Document bugs and fixes | 4 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 14 | 14
Documentation | Prepare requirements documentation (SRS) | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 20 | 20
| Create design document | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 20 | 20
| Prepare user manual | 4 | 1 | 4 | 1 | 4 | 1 | 4 | 1 | 4 | 1 | 14 | 14
| Finalize project report | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 14 | 14
Overhead | Project Management | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 20 | 20
| Risk management and mitigation tracking | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 3 | 1 | 1 | 8 | 7
| Communication with professor/grader | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5
| Preparing presentations and status reports | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 14 | 14
TOTAL ESTIMATED and ACTUAL EFFORT per student |  | 85 | 57 | 84 | 59 | 84 | 54 | 85 | 57 | 80 | 53 | 412 | 327